## 404 Execution
Execution Plan 1/16/2025-4/28/2025
| 2025-01-16 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-13 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-04-24 | Date
PCBv1s Design (Full Design Review) | [15 empty] | 2025-01-28
Status Update Presentation 1 | [12 empty] | Not Started |  |  | 2025-01-29
PCBv1s Order | [12 empty] | In Progress |  |  | 2025-02-06
Parts Order 4 | [12 empty] | Completed |  |  | 2025-02-11
Firmware Validation | [12 empty] | Behind Schedule |  |  | 2025-02-12
Status Update Presentation 2 | [15 empty] | 2025-02-12
Status Update Presentation 3 | [15 empty] | 2025-02-26
PCBv1s Assembly | [15 empty] | 2025-03-19
MCU/Firmware Integration | [15 empty] | 2025-03-19
Status Update Presentation 4 | [15 empty] | 2025-03-19
Auxilary Power Integration | [15 empty] | 2025-04-02
Status Update Presentation 5 | [15 empty] | 2025-04-02
PWM Control Integration | [15 empty] | 2025-04-03
Relay Control Integration | [15 empty] | 2025-04-07
System Integration | [15 empty] | 2025-04-07
System Testing | [15 empty] | 2025-04-16
Final Presentation | [15 empty] | 2025-04-16
Diagnostic Feedback Integration | [15 empty] | 2025-04-24
System Validation | [15 empty] | 2025-04-24
Final Demonstration | [15 empty] | 2025-04-24
Engineering Project Showcase | [15 empty] | 2025-04-25
Final Report | [15 empty] | 2025-04-28

## Validation_v0
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Speed and Torque Requirement | Motor shall operate within speed range of 0RPM to 1800RPM and torque range of 0lb-ft to 0.729lb-ft. | Input motor with voltage and check if it achieves 0RPM and 0lb-ft . Repeat for 300RPM, 600RPM, 900RPM, 1200RPM, 1500RPM, 1800RPM. | Untested | Andrew, Ryan
3.2.1.2 | Frequency Requirement | System shall operate within frequency range of 10Hz to 60Hz. | Input system with frequency generator set to 5Hz and check if the motor runs smoothly. Repeat for 10Hz, 20Hz, 30Hz, 40Hz, 50Hz, 60Hz. | Untested | All
3.2.1.3 | Temperature Requirement | System shall operate within temperature range of 0˚C to 70˚C. | Place system in freezer set to 0˚C and check if the motor runs smoothly. Repeat with oven set to 70˚C. | Untested | All
3.2.3.2 | Input Voltage Level | System input voltage shall be 208VAC. | Measure with multimeter and check if the voltage is 208VAC. | Untested | Aidan
3.2.3.3 | Input Noise and Ripple | System shall not exceed ripple range of 0V to 0.165V. | Measure with multimeter and check if the voltage exceeds 0V to 0.165V. | Untested | Andrew
3.2.3.4 | External Commands | External commands shall be documented in appropriate ICD. | Show to teaching team and check with them for approval. | Untested | All
3.2.3.5 | Visual Output | Oscilloscope displays each of the three phases of the PWM sine wave. | Connect oscilloscope probes to the set output pins for the PWM signals, ensure that the signals' duty cycles span from 0-100% and are rougly separated by thirds. | Tested | Ryan
3.2.3.6 | Connectors | System shall use terminal blocks for power and signal connections. | Observe power and signal connections and check if they are are terminal blocks. | Untested | Mackenzie, Andrew, Aidan
3.2.3.7 | Overtemperature Shutdown | System shall automatically shut down if sensor exceeds temperature range of 0˚C to 70˚C. | Place sensor in freezer set to -1˚C and check if sensor is triggered. Repeat with oven set to 71˚C. | Untested | Mackenzie
3.2.3.8 | Built in Test | System shall generate and evaluate test signals to assess failure status. | Compare generated values with known values and check if the failure statuses match. Repeat for six additional sets of values. | Untested | All
3.2.3.9 | Optoelectronics Voltage Constraint | The optoelectronics subsystem shall convert the voltage it receives down to a voltage in the range of 15-20 V. | Test at full power where the opto receives ~60 V. Use a multimeter to measure voltage level on other side of opto barrier. | Tested | Mackenzie
3.2.3.10 | Digital to Power Continuity | The digital to power opto-isolators shall have a voltage of 0V across each component when connecting input to output. | Use a multimeter to ensure that the voltage across each digital isolator is zero. | Tested | Mackenzie
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.3.11 | Power to Digital Continuity | The power to digital opto-isolators shall have a voltage of 0V across each component when connecting input to output | Use a multimeter to ensure that the voltage across each power isolator is zero. | Tested | Mackenzie
TBD | Inputs | The parameters are within the expected range. | Confirm that all electrical parameters (voltage, current, power) remain within safe and expected ranges under varying conditions. | Untested | All
TBD | Firmware Code Compiles | MPLab firmware successfully compiles without errors or warnings | Attempt to compile code in MPLab and examine output logs to check for errors or warnings | Tested | Ryan
TBD | Controller Performance | Motor spins according to user defined parameters. | Validate that the system operates efficiently and delivers accurate motor control across the expected range of operating conditions. | Untested | All
TBD | MCU Voltage Step Down | MCU converts the voltage it is given to 3.3V. | Measure the voltage of the signals being sent to the MCU and measure that the MCU converts it to 3.3V. | Untested | Mackenzie, Andrew
TBD | Rectifier Full System | System input voltage shall be rectified from 208VAC to 295VDC. | Measure with multimeter and check if the voltage after the rectifier is 295VDC. | Untested | Aidan
TBD | Rectifier Power Subsystem | System input voltage shall be rectified from 5VAC to 7.1 VDC. | Input 5VAC at differing angles of 120˚ on three waveform generators. Measure with multimeter and check if the voltage after the rectifier is 7.1 VDC. | Tested | Aidan
TBD | Isolated 15V Conversion | System shall convert 15VDC to isolated 15VDC. | Input 15VDC on a dc power supply. Measure with multimeter and check if the voltage after the converter is 15VDC. | Tested | Aidan
TBD | Isolated 5V Conversion | System shall convert 3.3VDC to isolated 5VDC. | Input 3.3VDC on a dc power supply. Measure with multimeter and check if the voltage after the converter is 5VDC. | Untested | Aidan
TBD | User Interface | User is able to change the speed of the rotating PWM values by turning the potentiometer. | Change potentiometer position to lowest, highest, and middle notch to observe that the target frequency of the system is close to 60, 10, and 35 respectively, and the rotating PWM values change pace accordingly | Tested | Ryan
TBD | Frequency Testing | Code properly changes the frequency of the PWM signals | Use oscilloscope or a timer to measure the PWM waves to ensure that the program's target frequency is similar to the actual frequency of the PWM signals. | Tested | Ryan
TBD | Debugger Connection | The Microcontroller shall be able to properly communicate with Pickit4 debugger | Connect the Pickit4 Debugger to microcontroller PCB using the 5 pin connector and ensure that MPLAB X IDE can recognize the device. | Untested | Andrew
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Input motor with _____ set with voltage to achieve
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Explain what quantity shows we know the motor is running smoothly. Probably a graph with slope to certain graduality.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Measure what?
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Measure what? Which pins on which component?
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Observe ______ and check if it is a terminal block. Repeat for _________.
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is this one?

## Validation_v1_rd
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.3.11 | 15 VDC to Isolated 15 VDC Conversion | Power converters shall convert 15 VDC to isolated 15 VDC. | Apply 15 VDC input using a DC power supply. Verify 15 VDC output using an oscilloscope. | Tested | Aidan | tested, fully validated | FSR 1 = Input Voltage Level aka 3.2.3.2; maybe add subdivisions to distinguish between input voltage level (208VAC) and component voltage (15V, 15V, 3.3V, 5V)
3.2.3.12 | 15 VDC to 3.3 VDC Conversion | Power converters shall convert 15 VDC to 3.3 VDC. | Apply 15 VDC input using a DC power supply. Verify 3.3 VDC output using an oscilloscope. | Tested | Drew | tested, not fully validated
3.2.3.13 | 3.3 VDC to Isolated 5 VDC Conversion | Power converters shall convert 3.3 VDC to isolated 5 VDC. | Apply 3.3 VDC input using a DC power supply. Verify 5 VDC output using an oscilloscope. | Tested | Aidan | tested, fully validated
3.2.3.14 | Low Voltage Auxiliary Power | System shall convert 15 VDC to isolated 15 VDC , 3.3 VDC, and isolated 5 VDC. | Apply 15 VDC input using a DC power supply. Verify 15 VDC , 3.3 VDC, and 5 VDC outputs using an oscilloscope. | Tested | Mackenzie, Drew, Aidan | tested, not fully validated, provide data in final presentation
3.2.3.15 | 120 VAC to 15 VDC Conversion | Power converters shall convert 120 VAC to isolated 15 VDC. | Apply 120 VAC input using a 120 VAC outlet. Verify 15 VDC output using an oscilloscope. | Tested | Drew | tested, not fully validated
3.2.3.16 | 120 VAC Auxiliary Power | System shall convert 120 VAC to 15 VDC, isolated 15 VDC , 3.3 VDC, and isolated 5 VDC. | Apply 120 VAC input using a 120 VAC outlet. Verify 15 VDC, 15 VDC , 3.3 VDC, and 5 VDC outputs using an oscilloscope. | Tested | Mackenzie, Drew, Aidan | tested, not fully validated
3.2.3.17 | Relay | Relay shall toggle the motor with the relay signal. | Apply 15 VDC coil voltage, 10 VDC contact voltage, and 5 VDC relay signal using a DC power supply. Verify 10 VDC output using an oscilloscope. | Tested | Aidan | tested, not fully validated | FSR 2 = new requirement to require on/off functionality
3.2.3.18 | Relay Signal Isolation | Digital to power shall convert the relay signal from 3.3 VDC to 5 VDC. | Apply 5 VDC supply voltage, 3.3 VDC supply voltage, and 3.3 VDC relay signal using a DC power supply. Verify 5 VDC output using an oscilloscope. | Tested | Mackenzie | tested, not fully validated
3.2.3.19 | Relay Signal Generation | MCU shall toggle the relay signal to 3.3 VDC with the button signal. | Apply 3.3 VDC supply voltage and 3.3 VDC button signal using a DC power supply. Verify 3.3 VDC output using an oscilloscope. | Tested | Drew, Ryan | tested, fully validated
3.2.3.20 | Firmware Relay Signal Generation | Dev board shall toggle the relay signal to 3.3 VDC with the button signal. | (On the dev board) Apply 3.3 VDC supply voltage and 3.3 VDC button signal using a DC power supply. Verify 3.3 VDC output using an oscilloscope. | Tested | Ryan | tested, fully validated
3.2.3.21 | Button Signal Generation | Button shall toggle the button signal to 3.3 VDC with a button press. | Apply 3.3 VDC supply voltage using a DC power supply and initiate a button press. Verify 3.3 VDC output using an oscilloscope. | Tested | Drew | tested, fully validated
3.2.3.22 | On/Off Button | System shall toggle the motor between on and off state with a button press. | Apply 15 VDC coil voltage, 10 VDC contact voltage, 5 VDC supply voltage, and 3.3 VDC supply voltage using a DC power supply. Initiate one button press and later a second button press. Verify the motor rotates after the first button press and stops after the second button press using a video. | Tested | All | tested, fully validated
3.2.3.23 | 10 VAC to 12 VDC Rectification | Rectifier shall convert 120 VAC to 112 VDC. | Apply 120 VAC input using a 120 VAC outlet. Verify 112 VDC output using an oscilloscope. | Tested | Aidan
3.2.3.24 | 120 VAC to 112 VDC Rectification | Rectifier shall convert 120 VAC to 112 VDC. | Apply 120 VAC input using a 120 VAC outlet. Verify 112 VDC output using an oscilloscope. | Tested | Aidan | tested, without proof | FSR 3 = motor to run at 208 VAc aka inout voltage level aka 3.2.3.2
3.2.3.25 | Power Control | Power control shall invert three high and three low 5 VDC PWM signals into three modified sine waves. | Apply 40 VDC bus voltage and 15 VDC supply voltage using a DC power supply. Apply three high and three low 5 VDC PWM signals at 120˚ phase shifts using a function generator. Verify three modified sine waves at 120˚ phase shifts using an oscilloscope. | Tested | Aidan | tested, without proof | FSR 4 = pwm signals
3.2.3.26 | PWM Signal Isolation | Digital to power shall convert three high and three low PWM signals from 3.3 VDC to 5 VDC. | Apply isolated 5 VDC supply voltage and 3.3 VDC supply voltage using a DC power supply. Apply three high and three low 3.3 VDC PWM signals at 120˚ phase shifts using a function generator. Verify three high and three low 5 VDC PWM signals at 120˚ phase shifts using an oscilloscope. | Tested | Mackenzie | tested, not fully validated
3.2.3.27 | PWM Signal Generation | MCU shall generate three high and three low 3.3 VDC PWM signals with the knob signal. | Apply 3.3 VDC supply voltage and 3.3 VDC speed knob signal using a DC power supply. Verify three high and three low 3.3 VDC PWM signals at 120˚ phase shifts using an oscilloscope. | Tested | Drew, Ryan | tested, fully validated
3.2.3.28 | Knob Signal Generation | Rotating potentiometer changes frequency to speed up and slow down motor. | Oscilloscope each signal output, spin knob and ensure the motor speed varies as expected. | Tested | Drew, Ryan | tested, fully validated
3.2.3.29 | Firmware PWM Signal Generation | Dev board shall generate three high and three low 3.3 VDC PWM signals with the knob signal. | (On dev board) Apply 3.3 VDC supply voltage and 3.3 VDC speed knob signal using a DC power supply. Verify three high and three low 3.3 VDC PWM signals at 120˚ phase shifts using an oscilloscope. | Tested | Ryan | tested, fully validated
3.2.3.30 | Firmware Knob Signal Generation | Rotating dev board potentiometer changes frequency to speed up and slow down motor. | (On dev board) Oscilloscope each signal output, spin knob and ensure the motor speed varies as expected. | Tested | Ryan | tested, fully validated
3.2.3.31 | Low Voltage PWM Control | System shall change the motor speed with the knob signal. | Apply 40 VDC bus voltage, 15 VDC supply voltage, isolated 5 VDC supply voltage and 3.3 VDC supply voltage using a DC power supply. Verify the motor rotates at a different speed after a knob turn using a video. | Tested | All | tested, not fully validated, provide data in final presentation
3.2.3.32 | 112 VDC PWM Control | System shall change the motor speed with the knob signal. | Apply 112 VDC bus voltage, 15 VDC supply voltage, isolated 5 VDC supply voltage and 3.3 VDC supply voltage using a DC power supply. Verify the motor rotates at a different speed after a knob turn using a video. | Untested | All
3.2.3.33 | Motor On/Off Signal Generation | MCU shall toggle the motor on/off LED signal to 3.3 VDC with the button signal. | Directly inject 15V to MCU and use multimeter at the motor LED via. | Tested | Drew, Ryan | tested, not fully validated | FSR 5 = motor on/off led
3.2.3.34 | Motor On/Off LED | System shall toggle the motor on/off LED between on and off states with the motor on/off signal. | Directly inject 15V to MCU, then press relay toggle button and ensure the motor LED toggles. | Tested | Drew, Ryan | tested, not fully validated
3.2.3.35 | System On/Off Signal Generation | MCU shall toggle the circuit on/off LED signal to 3.3 VDC when the board receives power. | Directly inject 15V to MCU and use multimeter at the system LED via. | Tested | Drew, Ryan | tested, not fully validated | FSR 6 = circuit on/off led
3.2.3.36 | System On/Off LED | System shall toggle the circuit on/off LED when the board is connected to power with the circuit on/off signal | Directly inject 15V to MCU and ensure the system LED turns on. | Tested | Drew, Ryan | tested, not fully validated
3.2.3.37 | Firmware Motor On/Off LED Signal Generation | Firmware shall toggle the dev board's on/off LED signal to 3.3 VDC with the button signal. | Directly inject 15V to dev board and use multimeter at the motor LED via. | Tested | Ryan | tested, fully validated
3.2.3.38 | Firmware Motor On/Off LED | Firmware shall toggle the dev board's on/off LED between on and off states with the motor on/off signal. | Directly inject 15V to dev board, then press relay toggle button and ensure the motor LED toggles. | Tested | Ryan | tested, fully validated
3.2.3.39 | Firmware System LED Signal Generation | Firmware shall toggle the dev board's on/off LED signal to 3.3 VDC when the board receives power. | Directly inject 15V to dev board and use multimeter at the system LED via. | Tested | Ryan | tested, fully validated
3.2.3.40 | Firmware System LED | Firmware shall toggle the dev board's on/off LED when the board is connected to power with the circuit on/off signal | Directly inject 15V to dev board and ensure the system LED turns on. | Tested | Ryan | tested, fully validated
3.2.3.41 | Computer Display | MCU will display diagnostic feedback information to the UART console on a computer running MPLAB X IDE. | Connect system to MPLAB X IDE using a laptop and USB-UART cable. Verify diagnostic print statements are being output to UART console. | Untested | Drew, Ryan |  | FSR 7 = diagnostic feedback
3.2.3.42 | Diagnostic Feedback Signal Isolation | Diagnostic feedback circuit shall transport the voltage, current, and temperature signals from across the isolation barrier to the MCU. | Apply 15 VDC supply voltage, isolated 15 VDC supply voltage, and three 15 VDC feedback signals using a DC power supply. Verify three 15 VDC outputs using an oscilloscope. | Untested | Mackenzie
3.2.3.43 | Diagnostic Feedback Signal Generation | Power Control shall generate 60 VDC voltage, current, and temperature feedback signals. | Apply 40 VDC bus voltage and 15 VDC supply voltage using a DC power supply. Apply three high and three low 5 VDC PWM signals at 120˚ phase shifts using a function generator. Verify three 60 VDC outputs using an oscilloscope. | Untested | Aidan
3.2.3.44 | Diagnostic Feedback | System shall send the voltage, current, and temperature signals to the computer display. | Each feedback signal will be verified through the UART console output. | Untested | All
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Motor slows to a stop when potentiometer is rotated more than halfway toward slow direction
Note on I21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Motor slows to a stop when potentiometer is rotated more than halfway toward slow direction

## Project Timeline
2025-02-12 | 2025-02-19 | 2025-03-07 | 2025-03-19 | 2025-04-02 | 2025-04-16 | 2025-04-28
Subsystem PCBv1 Designs & Testing | Auxiliary Power & MCU/Firmware Integration | PWM Control Integration | System Integration | System Testing | System Validation | Demo, Showcase, & Report

## 403 Execution
Exexcution Plan 8/20/2024-12/5/2024
| 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | Date
CONOPS Report | [16 empty] | 2024-09-15
FSR, ICD, Milestones, & Validation Plan | [12 empty] | Not Started |  |  |  | 2024-09-26
Firmware: GUI Development/Testing | [12 empty] | In Progress |  |  |  | 2024-09-24
Project Introduction Presentation | [12 empty] | Completed |  |  |  | 2024-09-30
Optoelectronics: Subsystem Introduction Project | [12 empty] | Behind Schedule |  |  |  | 2024-10-07
Microcontroller: Subsystem Introduction Project | [16 empty] | 2024-10-07
Parts Order 1 | [16 empty] | 2024-10-08
Power: Subsystem Introduction Project | [16 empty] | 2024-10-14
Firmware: Subsystem Introduction Project | [16 empty] | 2024-10-15
Firmware: Develop Outline | [16 empty] | 2024-10-15
Project Update Presentation | [16 empty] | 2024-10-21
Firmware: Add Debug Print Statements to Outline | [16 empty] | 2024-10-22
Firmware: Write to Demo Each Component Needed | [16 empty] | 2024-10-22
Firmware: Single-Phase Potentiometer Duty Cycle Control | [16 empty] | 2024-10-29
Optoelectronics: Schematic Layout | [16 empty] | 2024-10-29
Power: DC Link Schematic Layout | [16 empty] | 2024-11-02
Power: Rectifier Schematic Layout | [16 empty] | 2024-11-03
Power: Power Control Schematic Layout | [16 empty] | 2024-11-04
Microcontroller: Schematic Layout | [16 empty] | 2024-11-04
Optoelectronics: PCB Layout | [16 empty] | 2024-11-05
Microcontroller: PCB Layout | [16 empty] | 2024-11-05
Power: PCB Layout | [16 empty] | 2024-11-05
Optoelectronics: Order PCB | [16 empty] | 2024-11-05
Microcontroller: Order PCB | [16 empty] | 2024-11-05
Power: Order PCB | [16 empty] | 2024-11-05
Parts Order 2 | [16 empty] | 2024-11-12
Optoelectronics: PCB Assembly | [16 empty] | 2024-11-18
Microcontroller: PCB Assembly | [16 empty] | 2024-11-18
Power: PCB Assembly | [16 empty] | 2024-11-18
Firmware: Convert PWM signal to three-phase | [16 empty] | 2024-11-18
Final Presentation | [16 empty] | 2024-11-18
Optoelectronics: Validation/Debugging | [16 empty] | 2024-11-26
Microcontroller: Validation/Debugging | [16 empty] | 2024-11-26
Power: Validation/Debugging | [16 empty] | 2024-11-26
Firmware: Validation/Debugging | [16 empty] | 2024-11-26
Project Subsystem Demonstration | [16 empty] | 2024-11-26
Final Report | [16 empty] | 2024-12-05